## Sheet1
Type | Task | EDC (days) | ADC (days)
Module | aVX | 7
Module | Empty Recipe | 3
Module | Alarm Listener | 2 | 2
Module | Bypass Equipment
Translation | Operation | 1 | 1
Translation | Default Settiings | 1 | 1
Translation | Schematics | 1 | 1
UI | Operation Door Button | 1 | 1
UI | Recipe Management
UI | Range Slider
UI | Default Settings
UI | Operation
Page | Knowledge Base
Page | Version
Page | Credits
|  |  |  | EDC - Estimated Duration of Completion | Completed
|  |  |  | ADC - Actual Duration of Completion | In Progress
To be completed